## Product Backlog
Priority | Item # | Description | Estimate by Hours | Remaining Hours By Sprint Start
|  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
Very High Priority | 1 | Product Vision | 120 | 120 | 20 | 0 | 0 | 0 | 0 | 0 | 0
| 2 | Use Case Details | 120 | 120 | 70 | 0 | 0 | 0 | 0 | 0 | 0
| 3 | Product Selection | 200 | 200 | 180 | 120 | 0 | 0 | 0 | 0 | 0
| 4 | Prices Comparison | 120 | 120 | 120 | 100 | 80 | 0 | 0 | 0 | 0
| 5 | Testing | 160 | 160 | 160 | 160 | 140 | 120 | 90 | 70 | 60
High Priority | 6 | Deals for specific merchant | 24 | 24 | 24 | 24 | 24 | 24 | 0 | 0 | 0
| 7 | Wishlist | 80 | 80 | 80 | 80 | 80 | 50 | 10 | 0 | 0
| 8 | DB Design | 40 | 40 | 40 | 40 | 40 | 40 | 0 | 0 | 0
| 9 | Save Comparison | 40 | 40 | 40 | 40 | 40 | 0 | 0 | 0 | 0
| 10 | User Authentication | 56 | 56 | 56 | 56 | 56 | 56 | 56 | 46 | 0
| 11 | Product Reviews | 96 | 96 | 96 | 96 | 96 | 96 | 50 | 10 | 0
| 12 | Daily Customised Product Alerts | 80 | 80 | 80 | 80 | 80 | 80 | 70 | 30 | 0
| 13 | Manage Account | 64 | 64 | 64 | 64 | 64 | 64 | 64 | 44 | 0
| 14 | Design Layout | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 20
| 15 | Price trends Product wise | 64 | 64 | 64 | 64 | 64 | 64 | 64 | 54 | 10
| 16 | Bug Fixes | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 60 | 60
TOTALS |  |  | 1368 | 1368 | 1198 | 1028 | 868 | 689 | 508 | 338 | 150

## Sprint Backlog
| SPRINT 1 |  |  |  | SPRINT 2 |  |  |  | SPRINT 3 |  |  |  | SPRINT 4 |  |  |  | SPRINT 5 |  |  |  | SPRINT 6 |  |  |  | SPRINT 7 |  |  |  | SPRINT 8
Days Left In Iteration -----> |  | 14 | 7 | 0 |  | 14 | 7 | 0 |  | 14 | 7 | 0 |  | 14 | 7 | 0 |  | 14 | 7 | 0 |  | 14 | 7 | 0 |  | 14 | 7 | 0 |  | 11 | 0
Description | Status | 2016-01-12 | 2016-01-19 | 2016-01-25 | Status | 2016-01-26 | 2016-02-02 | 2016-02-08 | Status | 2016-02-09 | 2016-02-16 | 2016-02-22 | Status | 2016-02-23 | 2016-03-01 | 2016-03-07 | Status | 2016-03-08 | 2016-03-15 | 2016-03-21 | Status | 2016-03-22 | 2016-03-29 | 2016-03-04 | Status | 2016-04-05 | 2016-04-12 | 2016-04-18 | Status | 2016-04-19 | 2016-04-30
Product Vision | In Progress | 120 | 60 | 20 | Completed | 20 | 0 | 0 | Completed | 0 | 0 | 0 | Completed | 0 | 0 | 0 | Completed | 0 | 0 | 0 | Completed | 0 | 0 | 0 | Completed | 0 | 0 | 0 | Completed | 0 | 0
Use Case Details | In Progress | 120 | 100 | 70 | Completed | 70 | 30 | 0 | Completed | 0 | 0 | 0 | Completed | 0 | 0 | 0 | Completed | 0 | 0 | 0 | Completed | 0 | 0 | 0 | Completed | 0 | 0 | 0 | Completed | 0 | 0
Product Selection | In Progress | 200 | 196 | 180 | In Progress | 180 | 160 | 120 | Completed | 120 | 60 | 0 | Completed | 0 | 0 | 0 | Completed | 0 | 0 | 0 | Completed | 0 | 0 | 0 | Completed | 0 | 0 | 0 | Completed | 0 | 0
Prices Comparison | Not Started | 120 | 120 | 120 | In Progress | 120 | 110 | 100 | In Progress | 100 | 90 | 80 | Completed | 80 | 40 | 0 | Completed | 0 | 0 | 0 | Completed | 0 | 0 | 0 | Completed | 0 | 0 | 0 | Completed | 0 | 0
Testing | Not Started | 160 | 160 | 160 | Not Started | 160 | 160 | 160 | In Progress | 160 | 150 | 140 | In Progress | 140 | 130 | 120 | In Progress | 120 | 100 | 90 | In Progress | 90 | 80 | 70 | In Progress | 70 | 75 | 60 | Completed | 60 | 0
Deals for specific merchant | Not Started | 24 | 24 | 24 | Not Started | 24 | 24 | 24 | Not Started | 24 | 24 | 24 | Not Started | 24 | 24 | 24 | Completed | 24 | 12 | 0 | Completed | 0 | 0 | 0 | Completed | 0 | 0 | 0 | Completed | 0 | 0
Wishlist | Not Started | 80 | 80 | 80 | Not Started | 80 | 80 | 80 | Not Started | 80 | 80 | 80 | In Progress | 80 | 65 | 50 | In Progress | 50 | 30 | 10 | Completed | 10 | 50 | 0 | Completed | 0 | 0 | 0 | Completed | 0 | 0
DB Design | Not Started | 40 | 40 | 40 | Not Started | 40 | 40 | 40 | Not Started | 40 | 40 | 40 | Not Started | 40 | 40 | 40 | Completed | 40 | 20 | 0 | Completed | 0 | 0 | 0 | Completed | 0 | 0 | 0 | Completed | 0 | 0
Save Comparison | Not Started | 40 | 40 | 40 | Not Started | 40 | 40 | 40 | Not Started | 40 | 40 | 40 | Not Started | 40 | 40 | 0 | Completed | 0 | 0 | 0 | Completed | 0 | 0 | 0 | Completed | 0 | 0 | 0 | Completed | 0 | 0
User Authentication | Not Started | 56 | 56 | 56 | Not Started | 56 | 56 | 56 | Not Started | 56 | 56 | 56 | Not Started | 56 | 56 | 56 | Not Started | 56 | 56 | 56 | In Progress | 56 | 50 | 46 | Completed | 46 | 20 | 0 | Completed | 0 | 0
Product Reviews | Not Started | 96 | 96 | 96 | Not Started | 96 | 96 | 96 | Not Started | 96 | 96 | 96 | Not Started | 96 | 96 | 96 | In Progress | 96 | 76 | 50 | In Progress | 50 | 30 | 10 | Completed | 10 | 8 | 0 | Completed | 0 | 0
Daily Customised Product Alerts | Not Started | 80 | 80 | 80 | Not Started | 80 | 80 | 80 | Not Started | 80 | 80 | 80 | Not Started | 80 | 80 | 80 | In Progress | 80 | 75 | 70 | In Progress | 70 | 50 | 30 | Completed | 30 | 15 | 0 | Completed | 0 | 0
Manage Account | Not Started | 64 | 64 | 64 | Not Started | 64 | 64 | 64 | Not Started | 64 | 64 | 64 | Not Started | 64 | 64 | 64 | Not Started | 64 | 64 | 64 | In Progress | 64 | 54 | 44 | Completed | 44 | 22 | 0 | Completed | 0 | 0
Design Layout | Not Started | 24 | 24 | 24 | Not Started | 24 | 24 | 24 | Not Started | 24 | 24 | 24 | Not Started | 24 | 24 | 24 | Not Started | 24 | 24 | 24 | Not Started | 24 | 24 | 24 | In Progress | 24 | 24 | 20 | Completed | 20 | 0
Price trends Product wise | Not Started | 64 | 64 | 64 | Not Started | 64 | 64 | 64 | Not Started | 64 | 64 | 64 | Not Started | 64 | 64 | 64 | Not Started | 64 | 64 | 64 | In Progress | 64 | 59 | 54 | In Progress | 54 | 24 | 10 | Completed | 10 | 0
Bug Fixes | Not Started | 80 | 80 | 80 | Not Started | 80 | 80 | 80 | Not Started | 80 | 80 | 80 | Not Started | 80 | 80 | 80 | Not Started | 80 | 80 | 80 | In Progress | 80 | 70 | 60 | In Progress | 60 | 60 | 60 | Completed | 60 | 0
Total Estimated Hours Remaining |  | 1368 | 1284 | 1198 |  | 1198 | 1108 | 1028 |  | 1028 | 948 | 868 |  | 868 |  | 689 |  | 689 | 601 | 508 |  | 508 | 467 | 338 |  | 338 | 248 | 150 |  | 150 | 0